## Sheet1
Project Name : Cerpac
Start Date :July 26th, 2013
End Date : August 10th, 2013
Grace Period : 4 days
Launch Date : August 15th , 2013
Date | Task Name | Status | Assigned To | Estimate Hours | Start Date/Time | Finish Date/Time | Actual Hours | Predecessors | Notes(if any)
| 1.0 Design For Applicant | Assigned | Preyenka
| 2.0 Design For Admin | Assigned | Preyenka
| 3.0 Admin Refinement According to Cerpac | Assigned | Preyenka
4.0 Data Base Design and Flow
5.0 Replication Flow
| 6.0 Load Applicant Data | Assigned | Amit
| 6.1Insert Additional Fields | Assigned
| 6.2: Insert Zone Master In Applicant Module | Assigned
6.3 : Use Same Zone - Code as per Existing
6.4 : Create a title Master as per Existing
| 6.5 : Renewal Case : | Assigned | Amit
6.5.1 : Validate Based on Cerpac no , Fname , lname , dob
| 7.0 : Bank Module : | Assigned | Saurabh
7.1 Utility For Download
| 8.0 Requistion List | Assigned | Saurabh
8.1 Alter cerpac list to Requistion List in Exsiting
8.2 Insert Total no of postion
8.3 Collapsable Grid , Sorting according to Date ,desc ,asc
8.4 Maintain Status , Date of last Download.
8.5 Filter to Show Downloded / Un - Downloaded Data(check box)
| 9.0 Load Data from Bank data to Abuja Db | Assigned | Sudhakar
| 10.0 Command center | Assigned | Chitresh
10.1 preview secured FORM awaiting ( Grid will show all the secured form have not been converted in cerpec)
10.2 Generate File
11.0 Recommend
12.0 Auther & Issue
13.0 Productivity Mode
14.0 Immigration (quality Check)
| 15.0 Retrieval (FIND) | Assigned | Chitresh
15.1 according to Cerpac no , First Name , last name , company code , nationality , passport